## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Write down the clienet srory as ponits | 1 | Abrar | comblete | 1 | 2 | 0 | 0 | 0 | 0 | 0
Drow the UML diegram | 3 | Riyad | comblete | 3 | 3.5 | 0 | 1 | 0 | 1 | 0.5
Upedate the requierment | 2 | Abrar | In prosses | 1 | 1 | 2 | 0 | 0 | 0 | 0.5
Review the UML and Make sure about the relationships between classes in UML. | 2 | Riyad | Comblete | 2 | 0.5 | 1.5 | 0 | 0 | 0 | 0.5
Set the classes in Java | 3 | Riyad | Comblete | 4 | 0 | 2.5 | 1 | 0.5 | 2 | 1
User Story #2
work on class that ginarete the locations and save them in file | 5 | Riyad | Comblete | 6 | 0 | 3 | 2.5 | 4 | 0.5 | 1
Work on class that read the file and insort them into primery queue | 5 | Abrar | In prosses | 6 | 2 | 0 | 4 | 3 | 1 | 2
Review team member works | 1 | Mohammed | Comblete | 2 | 1 | 0 | 0 | 0 | 2 | 0
preint representations of the neighborhood | 6 | Mohammed | In prosses | 8 | 0 | 0 | 3 | 2 | 1 | 1
TOTAL |  |  |  | 33 | 10 | 9 | 11.5 | 9.5 | 7.5 | 6.5

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0